## Sheet1
Task | Time | Risk (1-5) | Assigned | Actual Time | Code Complete | Reviewer
C Coding Standard Rough Draft | 1 hour | 3 | Brandon | 1 hour | 100% | Nick
C Coding Standard Final Paper | 1 hour | 4 | All | NA | 50% | All
Create GitHub Repository | 10 min | 3 | Nick | 10 min | 100% | Skylar
Setup Directories in Repository | 20 min | 3 | Skylar | NA | 25% | Nick